## Sheet1
Estimated Hours: | 75 | See below for calculation of estimation
Individual Hours: | 15
Actual Hours:
|  | Date: | Regan | Date: | Andrew | Date: | Jui | Date: | Chen | Date: | Natasha
|  | 2021-10-14 | 0.5 | 2021-10-14 | 0.5 | 2021-10-14 | 0.5 | 2021-10-15 | 1 | 2021-10-14 | 0.5
|  | 2021-10-15 | 4 |  |  | 2021-10-21 | 2 | 2021-10-26 | 4 | 2021-10-15 | 1
|  | 2021-10-19 | 5 |  |  | 2021-10-27 | 0.5 |  |  | 2021-10-27 | 0.5
|  | 2021-10-25 | 3 |  |  | 2021-10-30 | 0.5 |  |  | 2021-10-31 | 1.5
|  | 2021-10-26 | 1 |  |  | 2021-10-31 | 3.5
|  | 2021-10-27 | 4
|  | 2021-10-28 | 7
|  | Total: | 24.5 |  | 0.5 |  | 7 |  | 5 |  | 3.5
|  | Total Hours: | 40.5
Total Lines of code for project 1: | 958 | <-- includes all lines of codes including comments
Total Hours on project | 63
LOC/hr | 15.2063 | - not necessarily accurate for LOC/hr since the total hours also included the time spent on other aspects of the project, but for estimation will assume those hours will be the same time spent for this project
Total Lines of code for project 2: | 500 | <-- this is rough estimate from the added lines of code to all 3 files. A lot of the hours for this project were spent of trying new ways to implement into the inherited groups project so just an LOC calculation probably isn't the best but it helps give a good estimate
Total Hours on project | 103
LOC/hr | 4.8544
Average LOC/hr | 10.0304
Estimate of Total LOC for project 3: | 750 | <-- this is an estimate based on the lines of code from the previous projects, we believe this project will be somewhere in between the previous two
750 LOC / 10.03 avg LOC/hr | 74.773 | <-- estimate of hours required for this project. This seems to be a better estimate than previous projects as we now know that a lot of time goes into the project aside from just writing code